# Glowfiesta 2026 - Event Owners Playbook

Glowfiesta, our office Diwali celebration, runs for four days from 2 to 5 November with five activities, and every activity is run by a small owner team. This playbook tells each owner team what is expected, when, and how to plan.

## Overview

- 2 Nov: Quiz 2.0

- 3 Nov: Funtakshri 3.0

- 4 Nov: Treasure Hunt 2.0

- 5 Nov (afternoon): Main Day decoration event, judged at 4:00 PM

- 5 Nov (evening): Evening event, anchored by three hosts

Each event has owners who form a small team of 1-2 people (3 for Treasure Hunt). The owners prepare everything: the rules, how to play, the tools needed, and the flow on the day.

## Schedule at a glance

Days 1-3 start at 5:30 PM; the Main Day starts at 12:00 PM.

| Date | Event | Start time | Owner team |
| --- | --- | --- | --- |
| 2 Nov | Quiz 2.0 | 5:30 PM | Kailash Kateja, Pankaj Toshniwal |
| 3 Nov | Funtakshri 3.0 | 5:30 PM | Vinod Gour, Ankit Jain |
| 4 Nov | Treasure Hunt 2.0 | 5:30 PM | Pradeep Kumar Sharma, Shubham Shah, Chirag Paneri |
| 5 Nov | Main Day: afternoon event (decoration) | 12:00 PM (judges arrive 4:00 PM) | 5 Main Day teams (see Owners and teams) |
| 5 Nov | Evening event | 5:30 PM | Hosts: Kritika Maroo, Amit Sharma, Sakshi Sandhya |

## Owners and teams

Each owner team may pull in 1-2 extra helpers if needed, and should tell the coordinator who they are.

| Event | Date | Owners |
| --- | --- | --- |
| Quiz 2.0 | 2 Nov | Kailash Kateja, Pankaj Toshniwal |
| Funtakshri 3.0 | 3 Nov | Vinod Gour, Ankit Jain |
| Treasure Hunt 2.0 | 4 Nov | Shubham Shah, Pradeep Kumar Sharma, Chirag Paneri |
| Main Day Team 1 | 5 Nov | Vinod Kumar Rangwani, Hemant Jain |
| Main Day Team 2 | 5 Nov | Abhishek Hingar, Kriti Sharma |
| Main Day Team 3 | 5 Nov | Vikas Kumar Mundra, Amit K Sharma |
| Main Day Team 4 | 5 Nov | Mayank Kothari, Tanushri Vaya |
| Main Day Team 5 | 5 Nov | Janmejay Duggar, Nitesh Kumar Garg |
| Evening event hosts | 5 Nov | Kritika Maroo, Amit Sharma, Sakshi Sandhya |

## What every owner team prepares

Each owner team is fully responsible for its event, from idea to wrap-up. Before your event day, have these ready:

- Format and flow: the full run of the event, minute by minute, within the 5:30 PM start.

- Rules and how to play: a one-page, easy-to-read rule sheet that participants can follow without asking.

- Teams and participation: how people join (individuals or teams), team size, and how teams are formed.

- Scoring and winners: how points are given, tie-break rule, who keeps the score, and the prizes or recognition.

- Tools and materials: projector, mic, laptop, slides, buzzers, props, printouts, stationery, and any app or website used.

- Venue and setup: the space needed, seating, and what must be set up before 5:30 PM.

- Helpers: who does what on the day (anchor, scorer, timekeeper, runner).

- Backup plan: what you do if a tool fails, time runs short, or turnout is higher than expected.

Share the plan using the template in this document so that the coordinator can review it before the event.

## Do's and Don'ts

Do

- Start on time: events begin at 5:30 PM (Main Day at 12:00 PM).

- Keep rules simple and share them clearly before play begins.

- Test every tool, mic and screen before participants arrive.

- Keep the activity inclusive so that everyone can take part.

- Tell the coordinator early if you need help, budget or space.

Don't

- Don't change the format on the day without informing the coordinator.

- Don't let one round or game run over its planned time.

- Don't use content that could offend anyone.

- Don't leave setup or clean-up to the last minute.